## TASKS

| Team Member | Primary Responsibility |
| --- | --- |
| Vassilis | Quality control, statistical analysis, theory |
| Sofia | All English data (YCOE, Penn if available) |
| Natasa | All Modern Greek data |
| Eleni | Classical + Koine + Byzantine Greek, coordination |
| Nikos | Training, decisions, synthesis, final write-up |

#### PHASE 1: Setup & Extraction

Vassilis:

- Review overall project design and verb selection

- Set up Python environment and test extraction scripts (1-2 hours)

- Troubleshoot any technical issues that arise

- Time commitment: 3-4 hours total

Sofia:

- Download YCOE corpus (Old English)

- Explore YCOE structure and identify Boethius translation

- Run test searches for English give-verbs (gifan, sellan)

- Document findings in shared spreadsheet

- Time commitment: 4-6 hours

Natasa:

- Download UD Modern Greek corpus

- Learn CoNLL-U format (follow beginner's guide section 2.3.0)

- Practice finding δίνω, λέω, φοβάμαι manually in text editor

- Create list of all Modern Greek sentences with target verbs

- Time commitment: 4-6 hours

Eleni:

- Download PROIEL corpus (Ancient/Koine Greek)

- Run full extraction script for Classical Greek (Plato + Herodotus)

- Run full extraction script for Koine Greek (New Testament)

- Extract Byzantine Greek (Sphrantzes) data

- Verify data completeness (all 12 verbs present)

- Help Natasa with Modern Greek extraction

- Time commitment: 6-8 hours

Nikos:

- Review extracted data from all team members

- Make final decisions on ambiguous verb instances

#### PHASE 2: Data Coding - Classical & Koine

Vassilis:

- Review coding scheme (Section 4)

- Code 50 sample tokens as quality control check

- Provide feedback on coding difficulties

- Time commitment: 3-4 hours

Sofia:

- Begin manual annotation of Old English data

- Focus on: gifan (give), secgan (say), sendan (send)

- Document frame types in spreadsheet

- Time commitment: 6-8 hours

Natasa:

- Complete extraction of Modern Greek data

- Begin annotation of Modern Greek give-verbs (δίνω, παρέχω)

- Focus on: identifying prepositional phrases (σε+ACC instead of dative)

- Time commitment: 6-8 hours

Eleni:

- Code all 12 verbs from Plato corpus

- Code all 12 verbs from Herodotus corpus

- Create detailed coding manual with examples as she works

- Document ambiguous cases for Nikos to review

- Time commitment: 10-12 hours

Nikos:

- Review Eleni's first 100 coded tokens

- Resolve ambiguous cases

- Check inter-coder agreement between Eleni and Vassilis samples

#### PHASE 3: Data Coding - Koine & Byzantine

Vassilis:

- Quality control: Review 10% of Eleni's Classical data

- Code challenging psych-verb cases from Koine

- Provide theoretical insights on argument structure changes

- Time commitment: 3-4 hours

Sofia:

- Complete Old English annotation

- Write summary: English valency patterns in OE Boethius

- If time permits: Begin Middle English sampling (PPCME2)

- Time commitment: 6-8 hours

Natasa:

- Complete Modern Greek annotation (all 12 verbs)

- Special focus: Note any colloquial vs. formal register differences

- Compare with Ancient Greek patterns (with Eleni's help)

- Time commitment: 6-8 hours

Eleni:

- Code all 12 verbs from New Testament

- Code all 12 verbs from Sphrantzes

- Note: φημί will be rare/absent by Byzantine period

- Cooperate with Natasa compare Ancient vs. Modern patterns

- Time commitment: 10-12 hours

Nikos:

- Review completed Classical data

- Check Koine/Byzantine coding as it progresses

- Statistical consultation

- Prepare for analysis phase

#### PHASE 4: Analysis & Write-up

Vassilis:

- Run statistical tests (chi-square for frame distribution changes)

- Interpret results from theoretical perspective

- Draft "Discussion" section for preliminary report

- Time commitment: 4-5 hours

Sofia:

- Compile English data summary

- Create comparative table: Greek vs. English diachronic changes

- Write "English Comparative Data" section

- Time commitment: 4-5 hours

Natasa:

- Create frequency tables for Modern Greek

- Prepare visualizations (bar charts) for Modern Greek patterns

- Write brief "Modern Greek Findings" section

- Time commitment: 4-5 hours

Eleni:

- Create master dataset (merge all periods)

- Generate frequency tables for each verb × period

- Create visualizations (graphs, heatmaps)

- Draft "Greek Diachronic Findings" section

- Proofread entire preliminary report

- Time commitment: 8-10 hours

- Note: Eleni coordinates final document but everyone contributes their sections

Nikos:

- Write introduction and methods sections

- Synthesize all team contributions

- Final editing of preliminary report

- Plan next steps (publication/conference abstract)

- Google Drive folder with:

  - Master spreadsheet (everyone adds their data)

  - Coding manual

  - Questions/issues log (anyone can add)

## DELIVERABLES

### Data Extraction

Deliverables:

- valency_data_classical.csv (Eleni)

- valency_data_koine.csv (Eleni)

- valency_data_byzantine.csv (Eleni)

- valency_data_modern.csv (Natasa)

### Data Coding (Part 1)

Deliverables:

- Annotated spreadsheet for Classical Greek - complete (Eleni, with Vassilis QC)

- Coding manual with examples v1.0 (Eleni drafts, team reviews)

- Old English data - 50% complete (Sofia)

- Modern Greek data - initial exploration (Natasa)

### Data Coding (Part 2)

Deliverables:

- Annotated spreadsheet for Koine Greek - complete (Eleni)

- Annotated spreadsheet for Byzantine Greek - complete (Eleni, with Vassilis backup if needed)

- Annotated spreadsheet for Modern Greek - complete (Natasa, with Eleni support)

- Old English annotation - complete (Sofia)

- Complete merged dataset (all Greek periods) (Eleni compiles)

- Inter-coder reliability check results (Vassilis + Nikos)

### Analysis & Visualization

Deliverables:

- Frequency tables for each verb × period (Eleni + Natasa)

- Statistical analysis report (Vassilis + Nikos)

- Visualizations: charts/graphs (Natasa for Modern, Eleni for Ancient/Koine/Byzantine)

- English comparative summary (Sofia)

- 2-3 page preliminary findings summary (All contribute sections, Nikos synthesizes)

Final Report:

- Introduction & Methods: Nikos

- Classical Greek Findings: Eleni

- Koine Greek Findings: Eleni

- Byzantine Greek Findings: Eleni

- Modern Greek Findings: Natasa

- English Comparative Data: Sofia

- Statistical Analysis: Vassilis

- Discussion & Theoretical Implications: Vassilis + Nikos

- Conclusion: Nikos

- Final editing & synthesis: Nikos (with Eleni proofreading)

### Comparative Analysis & Write-up (Optional Extension)

Tasks:

- Extract parallel data from English corpora

- Cross-linguistic comparison

- Draft conference abstract or paper outline

Deliverables:

- English valency data (if time permits)

- Comparative analysis report

- Conference abstract draft

### Tools

Required:

- Python 3.8+ (for XML parsing and data extraction)

  - Libraries: xml.etree.ElementTree, csv, pandas

- Spreadsheet software (Excel, Google Sheets, LibreOffice Calc)

- R or Python (for statistical analysis)

  - Python: pandas, scipy, matplotlib, seaborn

  - R: tidyverse, ggplot2, lme4

Optional:

- Corpus query tools: ANNIS, TGrep2 (for Penn Corpora queries)

- Database: SQLite (if managing large datasets)

- Visualization: Tableau, RAWGraphs (for publication-quality charts)